## Task List
User Story Estimation
Work Breakdow
Task # | Task | Time Estimation
1 | Create a page to display the greeting message | 5hr
2 | Create a text box to wait for the user input | 0.5hr
3 | Implement the functionality that allows the user to submit their text | 1hr
4 | Identify the central text to be analyzed from the user’s input if necessary | 0.5hr
5 | Create database to store all the text the user has submitted, in case of future reference | 3hr
6 | Prepare the text to be sent to OpenAI’s API | 0.5hr
7 | Communicate with OpenAI's api to analyze the text | 2hr
8 | Handle possible error messages returned from the api | 3hr
9 | Create proper feedback and notify the user what the particular error is | 1hr
10 | Support the functionality that allows the user to make any possible correction to their input | 1hr
11 | Create a page to display the 10 questions generated along with the original text | 0.5hr
12 | Wait and respond to further user interactions | 1hr